## Sheet1
Milestone | Task ID | Task Description | Deliverables Checklist | Comments | Done
Milestone 1: System Discovery, Architecture Design & Data Collection
| M1.1.1 | Establish secure VPN access to the live AAS system and document the process. |  |  | ☐
| M1.1.2 | Set up the Supabase project, including creating the database, enabling Auth, and configuring Storage buckets. |  |  | ☐
| M1.1.3 | Initialize the Git repository with a standard Next.js project structure and establish branching strategies (e.g., GitFlow). |  |  | ☐
| M1.1.4 | Create and document a local development environment for consistent setup across the team. |  |  | ☐
| M1.2.1 | Systematically review all AAS manuals (including Student, Event, and Visa modules) to create a comprehensive data dictionary mapping all entities, fields, and relationships. | - Produce a spreadsheet listing all data entities (Students, Schools, Events, etc.). - List all UI fields for each entity with data types and constraints. - List all possible values for every dropdown menu. - Document relationships between entities. |  | ☐
| M1.2.2 | Prepare Supabase Architecture | - Connection and access to Supabase |  | ☐
| M1.3.1 | Base Conception of Row Level Security (RLS) policies for key tables to enforce data access rules | - Conceptual Policy Designed |  | ☐
| M1.3.2 | Data Collection and Prepartion | - Collect All data from existing database - Prepare Test Data for Development |  | ☐
Milestone 2: Data Migration + Basic UI Creation
| M2.1.1 | Execute the secure extraction of all data from the legacy AAS database into a structured format (e.g., CSV, JSON). |  |  | ☐
| M2.1.2 | Develop the main application layout in Next.js, including a persistent navigation sidebar, header, and a protected route system that requires login. | - Responsive main layout with sidebar and header. - Application redirects unauthenticated users to login. - User's name and role displayed in the header. |  | ☐
| M2.2.1 | Implement the core user authentication system using Supabase Auth, including sign-in, sign-up (for admins), and password recovery flows. | - Functional login page authenticating against Supabase. - Admin interface for creating new user accounts. - 'Forgot Password' flow is implemented. |  | ☐
| M2.2.2 | Build the basic RLS policies for role-based access control, distinguishing between 'Administrator' and 'Consultant' roles. | - A function to check a user's role from a custom 'profiles' table. - API endpoints are protected by RLS policies. |  | ☐
Milestone 3: Core Web App - Student Management + Student Table Implementation
| M3.1 | Build the dynamic Student Dashboard page, featuring a responsive table to display all students, with real-time search and filter capabilities. | - Data table displays a list of all students. - Search input filters by Student ID, Surname, or Firstname. - Filter dropdowns for 'Case' and 'Officer'. |  | ☐
| M3.2 | Create the multi-tabbed 'Student Profile' page, replicating the 'Open new profile' view from the manual, to show all details for a selected student. | - Tabbed interface on the profile page. - 'Basic Info' tab displays all fields from the manual. - 'Contact' tab lists all parent/guardian contacts. - Placeholders for future tabs are present. |  | ☐
| M3.3 | Implement the 'Create New Student' and 'Edit Student' forms, ensuring all fields, data types, and validations from the AAS manual are covered. Connect these forms to the backend API. | - 'New Student' button opens a creation form. - Form includes all fields from the manual with validation. - 'Edit' button populates the form with existing student data. |  | ☐
| M3.4 | Implement Student Table |  |  | ☐
| M3.5 | Develop foundational Python scripts for extracting Student data and performing initial cleaning, formatting (e.g., SURNAMES to uppercase), and validation. | - Develop a Python script to read exported data. - Include functions to normalize data (uppercase, date formats, trim whitespace). - Implement a duplicate check for student records. |  | ☐
| M3.6 | Build the initial set of serverless functions (Supabase Functions) or API routes for CRUD (Create, Read, Update, Delete) operations on the Students table | - Full set of tested API endpoints for Students (getStudents, getStudentById, etc.). |  | ☐
Milestone 4: School & Application Management
| M4.1 | Build the 'School Database' module, allowing users to search, view, create, and edit school profiles. | - A searchable list of all schools is available. - Functionality to create and edit school profiles. |  | ☐
| M4.2 | Implement the tabbed interface within the School Profile, including 'Basic Info', 'Courses', and 'Entrance Exam' sections. | - 'School Profile' page has a tabbed interface. - 'Basic Info', 'Course', and 'Entrance Exam' tabs are functional. |  | ☐
| M4.3 | Develop the backend logic and database relationships to link Students with Schools via Applications. Create the necessary API endpoints. | - Backend logic and database relationships for applications are implemented. - API endpoints for applications are created and tested. |  | ☐
| M4.4 | Create the UI component on the Student Profile page for managing a student's school applications, including adding new applications and updating their status. | - 'School Application' tab on the student profile displays applications. - Users can add a new application for a student. - Users can update the status of an application. |  | ☐
| M4.5 | Set up a basic email notification system using Supabase Functions to trigger emails on application status changes. | - A serverless function to send emails is created. - The function uses a template for status change notifications. |  | ☐
Milestone 5: Visa Application Management
| M5.1 | Design and implement the database schema extension for Visa Management, linking visa details to student and school application records. | - 'Visa' table in the database is created with all required columns. - The table is correctly linked to student and application records. |  | ☐
| M5.2 | Build the 'Visa' tab within the Student Profile page, including the form to input application details (login, password, dates) and status checkboxes. | - A functional 'Visa' tab on the Student Profile page. - UI renders all checkboxes and fields as per the manual. - State is saved upon clicking a 'Save' button. |  | ☐
| M5.3 | Implement the backend logic to save, update, and retrieve visa application data and status. | - API endpoints (getVisaDetails, updateVisaDetails) are created and tested. |  | ☐
| M5.4 | Integrate document upload functionality specifically for visa-related documents within this tab, storing files in a designated 'visa' folder in Supabase Storage. | - A dedicated file upload area is present in the 'Visa' tab. - Uploaded files are associated with the specific visa record. |  | ☐
Milestone 6: Event, Exam & Booking Scheduler
| M6.1 | Integrate and configure the FullCalendar library to display consultant schedules, color-coded by booking type (AA Test, Consultation, etc.). | - A full-page calendar view is implemented. - Calendar displays all bookings from the database. - Bookings are color-coded correctly. | UI Done, dummy data color coded | ☐
| M6.2 | Develop the 'Make New Booking' feature, including a modal form for creating new appointments, selecting student, type, and time slots. | - Clicking a time slot opens a 'New Booking' modal. - The modal allows selection of all required booking parameters. - Test duration is calculated automatically for 'AA Test'. |  | ☐
| M6.3 | Build the 'Event Management' module (for Expos, Interviews) allowing admins to create events, add participating schools, and manage details. | - 'Events' section for creating and managing large-scale events. - Functionality to add event details, and associate schools/students. |  | ☐
| M6.4 | Implement the full 'Online Registration' workflow, including the backend logic to handle new sign-ups and prevent duplicate records. | - A public-facing registration page is created. - Internal page to view new submissions. - Duplicate student check is functional. - 'Save' button transfers the record correctly. |  | ☐
| M6.5 | Develop the 'Notice Setting' feature, allowing admins to create and display global announcements that appear on the main dashboard. | - Admin interface for creating 'Notices' with Type, Dates, and Contents. - A component on the main dashboard displays active notices. |  | ☐
Milestone 7: Document Management & PDF Generation
| M7.1 | Build a centralized 'Document Management' section in the Student Profile for uploading and categorizing general documents (e.g., reports, certificates). | - A 'Documents' tab on the Student Profile for general file uploads. - Files are deletable and downloadable. |  | ☐
| M7.2 | Replicate the 'Upload exam papers' workflow in the School Profile, associating PDF files with specific entrance exams. | - 'Entrance Exam' creation form includes 'Browse' and 'Upload Exam Paper' buttons. |  | ☐
| M7.3 | Develop a server-side function (using e.g., pdf-lib or a headless browser) to generate a basic PDF 'Student Summary' report from their profile data. | - A server-side function that takes a studentId as input. - The function generates a formatted PDF with student profile data. |  | ☐
| M7.4 | Create a button in the UI to trigger the PDF generation and download for the user. | - A 'Print Summary' button on the Student Profile triggers the function. |  | ☐
Milestone 8: QA + Alpha Testing
| M8.1 | Ensure smooth functionalities and test key flows (create student, print doc). |  |  | ☐
| M8.2 | Full QA run | - Data flow, UI checks, error handling - Mobile/responsive testing - Running manual and automated test flows. - Checking permissions, user roles, and data integrity. |  | ☐
Milestone 9: Testing, Deployment & Training
| M9.1.1 | Conduct thorough end-to-end testing of all critical user workflows, documenting results and tracking bugs. | - A completed test plan covering all major user stories. - A bug tracker report with resolution statuses. |  | ☐
| M9.1.2 | Organize and support User Acceptance Testing (UAT) sessions with the Academic Asia team. |  |  | ☐
| M9.2.1 | Implement critical bug fixes and refinements based on UAT feedback. |  |  | ☐
| M9.2.2 | Configure the production environments on Vercel and Supabase, including domain setup, environment variables, and automated backups. | - Production environment is fully configured. - Automated daily backups are configured and tested. |  | ☐
| M9.2.3 | Execute the final, full deployment to the live environment. |  |  | ☐
| M9.2.4 | Create comprehensive user training manuals and technical documentation for handover. | - A user manual with screenshots and step-by-step instructions. - Technical handover documentation. |  | ☐
| M9.3.1 | Conduct final training sessions for both administrator and consultant user groups. | - Record of completed training sessions with attendees. |  | ☐